Ava-SJCE 2026 Long-Term Resource RFO Attachment E.3

Energy Storage Services Agreement Term Sheet – Stand-alone Storage

This indicative term sheet (“Term Sheet”) is entered into as of _____, 2026 (the “Effective Date”) between [Ava Community Energy Authority, a California joint powers authority (“Ava” or “Buyer”)][City of San José, a California municipal corporation, administrator of San José Clean Energy (“SJCE” or “Buyer”)] and [Seller Name] (“Seller” or “Respondent”) in connection with the 2026 Long-Term Resource Request for Offers (“RFO”).  This Term Sheet is intended to summarize certain principal commercial terms and conditions to be included in a proposed energy storage services agreement (“ESSA”) between Seller and Buyer for the purchase and sale of the Product (the “Proposed Transaction”) from the Facility.  The definitive ESSA is expected to include additional and more detailed terms, conditions, representations, warranties, covenants, conditions precedent, and other provisions customary for transactions of this type and as required by Buyer. Negotiation of the ESSA is subject to Buyer selecting the Proposed Transaction for the negotiation shortlist, the terms and conditions of the RFO, timely execution of the Exclusive Negotiating Agreement (as defined below) and posting of the Shortlist Deposit (as defined in the Exclusive Negotiating Agreement) by Seller.  Except as expressly set forth in Section 2, no provision of this Term Sheet shall be binding or give rise to any legal obligation, express or implied, unless and until a definitive ESSA is approved by Seller’s management, [Ava/SJCE] management and the [Ava Board of Directors][San José City Council], as applicable, and executed and delivered by the Parties.

- ESSA Terms and Conditions.

| Seller: | [Seller Name, e.g., Project Company LLC] (“Seller”). As used in the ESSA, Buyer and Seller are each a “Party” and collectively the “Parties.” |  |
| --- | --- | --- |
| Description of Facility: | A [____] MW / [__] MWh grid-connected [insert description of storage technology here] energy storage facility (the “Facility”), located in [______] County, in the State of California. |  |
| Product: | “Product” includes the following: - Discharging Energy; - Storage Capacity; - Capacity Attributes (Full Capacity Deliverability Status); and - Ancillary Services; and For clarity, during the Delivery Term Seller may not use the Facility to provide services or attributes to any third party. |  |
| Storage Contract Capacity: | The Facility will have an initial Storage Capacity of [[XX] MW for four (4) hour discharge][[XX] MW for eight (8) hour discharge] (the “Storage Contract Capacity”). |  |
| Storage Degradation Schedule: | If applicable, the Storage Contract Capacity will degrade in accordance with the following annual schedule: Contract Year 1. Contract Year 2. Contract Year 3. Contract Year 4. …. |
| RA Capacity: | The Qualifying Capacity (QC) of the Facility, which is [XX] MW. |  |
| Interconnection Capacity: | The Facility has, or will have, an Interconnection Agreement providing for interconnection capacity available or allocable to the Facility that is no less than the Storage Contract Capacity. Seller shall ensure that, during the Delivery Term, Seller shall have sufficient interconnection capacity and rights under or through the interconnection agreement to interconnect the Facility with the CAISO-Controlled Grid and fulfill its obligations under the ESSA. Seller shall hold Buyer harmless from any penalties, Imbalance Energy charges, or other costs from CAISO or under the ESSA resulting from Seller’s inability to provide the foregoing interconnection capacity. |  |
| Scheduling Coordinator: | Buyer or Buyer’s agent shall act as Scheduling Coordinator for the Facility. |  |
| Delivery Term: | “Delivery Term” means [XX] Contract Years. |  |
| Storage Rate, Tolling Rate and Monthly Payment: | All Product shall be paid on a monthly basis at the Storage Rate multiplied by 1,000, multiplied by the current Storage Contract Capacity, as adjusted for the most recent Storage Capacity Test (as set forth in the ESSA), multiplied by the Round-Trip Efficiency Factor, and multiplied by the monthly Availability Adjustment for such month and pro-rated for the first and last month of the Delivery Term if the Delivery Term does not start on the first day of a calendar month. Such payment constitutes the entirety of the amount due to Seller from Buyer for the Product. In addition to adjustments pursuant to the Storage Capacity Test, the Storage Contract Capacity shall be reduced for each MW that is unavailable due to a Force Majeure Event lasting for more than five (5) consecutive days until such time as the Force Majeure Event ends for such Storage Capacity. If the Storage Contract Capacity is adjusted on any day other than the first day of a calendar month, payment shall be calculated separately for each portion of the month in which the different Storage Contract Capacity is applicable. The “Storage Rate” shall be [[XX]/kW-month], with no escalation. [Note: Seller may offer a price for 450 cycles per Contract Year. Seller may also offer a price for a top 4/bottom 4 approach in which case capacity products will be limited to Resource Adequacy and top 4/bottom 4 financial settlement.] |  |
| Guaranteed Efficiency Rate: | Contract Year; Guaranteed Round-Trip Efficiency. 1; 88.0%. 2 - End of Delivery Term; [Seller to fill out rest of table]. #### Liquidated Damages for Failure to Achieve Guaranteed Efficiency Rate: If during any month during the Delivery Term, the Efficiency Rate applicable to such month is less than the Guaranteed Efficiency Rate, Seller shall owe liquidated damages to Buyer, which damages shall be calculated by multiplying (i) the total Charging Energy for such month, by (ii) the percentage amount by which such applicable Efficiency Rate is less than the Guaranteed Efficiency Rate, by (iii) the simple average of the Day-Ahead Market locational marginal price for all On-Peak Hours of the applicable month, as published by the CAISO, for the Delivery Point, which amount shall be credited by Seller against amounts owed by Buyer in the applicable monthly invoice. |
| Performance-Related Events of Default: | #### The occurrence of any of the following shall constitute an Event of Default: #### if, in any two consecutive Contract Years, the average Monthly Storage Availability over the two-year period is less than seventy percent (70%); #### if, Seller fails to maintain an average Efficiency Rate equal or greater than the Minimum Efficiency Rate over a rolling 12-month period; #### if Ancillary Services, or any component thereof, are unavailable for any consecutive six-month period, except to the extent due to a Force Majeure Event; or #### if, Seller fails to maintain a Storage Contract Capacity equal to at least seventy-five percent (75%) of the initial Storage Contract Capacity for longer than three hundred sixty (360) days. |  |
| Deliverability: | The Facility will have Full Capacity Deliverability Status by the Commercial Operation Date. |  |
| Delivery Point: | “Delivery Point” means the point of interconnection with the CAISO-Controlled Grid, [insert name or location]. |  |
| Interconnection Point: | The Facility shall interconnect to [e.g., XX substation] (the “Interconnection Point”). Seller shall be responsible for all costs of interconnecting the Facility to the Interconnection Point. |  |
| Charging Energy: | Buyer is solely responsible, at Buyer’s sole cost, for procuring Charging Energy. |  |
| Station Use: | - Seller will be responsible for providing all station power and station use power will not be provided by the Facility. |  |
| Facility Development Milestones: | - [mm/dd/yyyy] – Execute interconnection agreement - [mm/dd/yyyy] – Procure major equipment - [mm/dd/yyyy] – Obtain federal and state discretionary permits - [mm/dd/yyyy] – Expected Construction Start Date - [mm/dd/yyyy] – Obtain Full Capacity Deliverability Status - [mm/dd/yyyy] – Expected Commercial Operation Date |
| Guaranteed Construction Start Date: | The “Guaranteed Construction Start Date” means the Expected Construction Start Date, subject to extensions on a day-for-day basis due to Force Majeure Event for a period of up to one hundred twenty (120) days on a cumulative basis (the “Development Cure Period”). For clarity, the permitted extensions under the Development Cure Period extend both the Guaranteed Construction Start Date and the Guaranteed COD simultaneously. Notwithstanding anything to the contrary, no extension shall be given under the Development Cure Period if, and to the extent that (i) the delay was due to Seller’s failure to take commercially reasonable actions to meet its requirements and deadlines or does not otherwise satisfy the requirements of a Force Majeure Event, (ii) Seller failed to provide requested documentation as provided below, or (iii) Seller failed to provide written notice of such Force Majeure Event to Buyer as required under the ESSA. Upon written request from Buyer, Seller shall provide documentation demonstrating to Buyer’s reasonable satisfaction that the delay was the result of a Force Majeure Event and did not result from Seller’s actions or failure to take commercially reasonable actions. In the event that Seller fails to achieve Construction Start on or before the Guaranteed Construction Start Date, Seller shall pay delay damages to Buyer in arrears on a monthly basis for each day of delay in the amount of One Thousand Forty-One Dollars and Sixty-Seven Cents ($1,041.67) per MW of Storage Contract Capacity per day (“Construction Delay Damages”). The Construction Delay Damages shall be refundable to Seller if, and only if, Seller achieves on or before the Guaranteed COD. Failure to achieve Construction Start for any reason, including a Force Majeure Event, within one hundred twenty (120) days of the Guaranteed Construction Start Date, shall constitute an Event of Default, and Buyer shall have the right, in its sole discretion, to terminate the ESSA and receive a damage payment in the amount of the Development Security (the “Damage Payment”). |
| Guaranteed Commercial Operation Date: | The “Guaranteed Commercial Operation Date” or “Guaranteed COD” means the Expected Commercial Operation Date, subject to extensions on a day-for-day basis for the Development Cure Period. If the Seller does not achieve COD of the Facility by the Guaranteed COD, Seller shall pay COD Delay Damages to the Buyer for each day of delay until Seller achieves COD. “COD Delay Damages” means an amount equal to Two Thousand Eighty-Three Dollars and Thirty-Three Cents ($2,083.33) per MW of Storage Contract Capacity per day. COD Delay Damages shall be paid for each day of delay and shall be paid to Buyer in advance on a monthly basis. A prorated amount will be returned to Seller if COD is achieved during the month for which COD Delay Damages were paid in advance. Failure to achieve COD for any reason, including a Force Majeure Event, within sixty (60) days of the Guaranteed COD, shall constitute an Event of Default, and Buyer shall have the right, in its sole discretion, to terminate the ESSA and receive the Damage Payment. For the avoidance of doubt, Seller’s liability for an Event of Default comprising the failure to timely achieve COD shall equal the sum of any Construction Delay Damages and COD Delay Damages that are due and owing, plus the Damage Payment. |
| Progress Reporting: | Seller shall provide a progress report (“Progress Report”) to Buyer on a quarterly basis until the Expected Construction Start Date, and on a monthly basis thereafter until the Commercial Operation Date; provided, that if Seller misses the Guaranteed Construction Start Date or Guaranteed Commercial Operation Date, Seller shall provide updated Progress Reports to Buyer on a weekly basis, or as otherwise agreed. Details regarding the form and content of the Progress Report will be attached to the ESSA as an exhibit. |
| Commercial Operation Date (“COD”): | The Commercial Operation Date shall be the later of (a) the Expected Commercial Operation Date or (b) the date on which the Facility has achieved commercial operation in accordance with the definitive ESSA, as reasonably determined by Buyer, following satisfaction of all applicable testing, interconnection, deliverability, and market participation requirements. The detailed conditions precedent, testing requirements, certifications, and procedures for achieving COD shall be set forth in the definitive ESSA, and shall include the following: - Seller has demonstrated functionality of the Facility’s communication systems and automatic generation control (AGC) interface to operate the Facility as necessary to respond and follow instructions, including an electronic signal conveying real time and intra-day instructions, directed by the Buyer in accordance with the ESSA and the CAISO; and - The Facility is fully capable of charging, storing and discharging energy up to no less than ninety-five percent (95%) of the Storage Contract Capacity and receiving instructions to charge, store and discharge energy, all within the operational constraints and subject to the applicable Operating Restrictions. Seller shall provide notice of expected COD to Buyer in writing no less than sixty (60) days in advance of such date. If Seller has not installed one hundred percent (100%) of the Storage Contract Capacity within one hundred twenty (120) days after the Commercial Operation Date, Seller shall pay Capacity Damages to Buyer for each MW that the Storage Contract Capacity exceeds the Installed Battery Capacity, and the Storage Contract Capacity and other applicable portions of the ESSA shall be adjusted accordingly. “Capacity Damages” means an amount equal to Two Hundred Fifty Thousand Dollars ($250,000) per MW. The Delivery Term shall not commence until Seller completes each of the following conditions precedent, which are intended to be illustrative and non-exclusive: - Seller has provided copies of all documentation required to be provided as a condition precedent to commencement of the Delivery Term, e.g., Interconnection Agreement, proof of insurance, satisfaction of other Seller commitments, etc.; - All applicable permits and government approvals required for the operation of the Facility have been obtained; - Seller has provided Buyer with a copy of written notice from the CAISO that the Facility has achieved Full Capacity Deliverability Status; - Seller has delivered the Performance Security to Buyer; and - Seller has paid Buyer all amounts owing under the ESSA as of such date, if any. Additional conditions precedent, procedural requirements, and documentation obligations will be set forth in the definitive ESSA. |
| Force Majeure: | Force Majeure is defined and addressed in the pro forma ESSA and shall apply consistently across all provisions of this Term Sheet. |
| Permits and Approvals: | Seller shall obtain any and all permits and approvals, including without limitation, environmental clearance under the California Environmental Quality Act (“CEQA”) or other environmental law, from the local jurisdiction where the Facility is or will be constructed. Buyer is simply purchasing power and does not intend to be the lead agency for the Facility. |
| Operations and Maintenance: | Subject to providing Buyer one hundred twenty (120) days’ prior Notice, Seller shall be permitted to reduce deliveries of Product during any period of scheduled maintenance on the Facility, provided that between June 1st and September 30th Seller shall not schedule non-emergency maintenance that reduces the storage capability of the Facility by more than ten percent (10%), unless (a) such outage is required to avoid damage to the Facility, (b) such maintenance is necessary to maintain equipment warranties and cannot be scheduled outside the Restricted Maintenance Period, (c) such outage is required in accordance with Prudent Operating Practices, or (d) the Parties agree otherwise in writing (each scheduled maintenance permitted under this clause and each of the foregoing outages described in foregoing clauses (a) – (d), a “Planned Outage”). Seller shall not replace existing batteries unless for critical maintenance purposes or increase the capacity of the Facility without the prior consent of Buyer. |
| Resource Adequacy Failure: | For each RA Shortfall Month, Seller shall pay to Buyer an amount equal to the RA Deficiency Amount. As used above: “Administrative NQC Reduction” means a reduction in the maximum achievable Net Qualifying Capacity of the Facility due to a reduction that has been generally applied to resources materially similar to the Facility in terms of generating technology and operational characteristics (including those characteristics specified in the CPUC Master Resource Database), including any methodology that incorporates fleet averages or other average outage rates. “Deemed Delivered RA” means for each hour of the Relevant Day in the applicable Showing Month the amount of Net Qualifying Capacity expressed in MW that the Facility would have delivered to the Delivery Point, but for (i) a Force Majeure Event, and (ii) Planned Outages permitted by the terms of the ESSA to the extent such Planned Outages reduce the maximum achievable Net Qualifying Capacity of the Facility. “Delivered RA” means for each hour of the Relevant Day in the applicable Showing Month the sum of (a) the Net Qualifying Capacity of the Facility for such month able to be shown on Buyer’s monthly or annual Resource Adequacy Plan to the CAISO and CPUC and counted as Resource Adequacy Capacity by both the CAISO and CPUC, (b) Deemed Delivered RA and (c) Replacement RA. “Guaranteed RA Amount” means the Qualifying Capacity minus Administrative NQC Reductions for each hour of the Relevant Day in the applicable Showing Month. “RA Deficiency Amount” means the liquidated damages payment that Seller shall pay to Buyer for an applicable RA Shortfall Month equal to the product of (i) the RA Shortfall Amount, and (ii) the Replacement Price. “RA Shortfall Amount” shall be determined by first, calculating the difference of the Guaranteed RA Amount minus the Delivered RA for each hour of the Relevant Day in the applicable Showing Month and, second, selecting the highest hourly difference for any hour of the Relevant Day in the applicable Showing Month as determined pursuant to step one of this calculation, which such highest hourly value shall be the “RA Shortfall Amount” for purposes of calculating an RA Deficiency Amount for such Showing Month; provided, if the CPUC adopts another methodology for calculating a load serving entity’s procurement deficiencies in Resource Adequacy Benefits for purposes of the Resource Adequacy Requirements, the Parties shall cooperate in good faith to amend this definition to conform to such new methodology in order to preserve to the maximum extent possible the benefits, burdens, and obligations set forth in this definition as of the Effective Date. If the result of the calculation is a negative number, the RA Shortfall Amount shall be deemed to be zero MW for such Showing Month. “RA Shortfall Month” means, for purposes of calculating an RA Deficiency Amount, any month commencing after the Commercial Operation Date during which there is an RA Shortfall Amount. “Relevant Day” means the peak day(s) of the month, or such other time period, as established by the CPUC for purposes of determining compliance with Resource Adequacy Requirements. “Replacement Price” means (a) the price at which Buyer, acting in a commercially reasonable manner, purchases a replacement for the Capacity Attributes not delivered by Seller, plus costs reasonably incurred by Buyer in purchasing such replacement Capacity Attributes, or at Buyer’s option, (b) the market price for such replacement Capacity Attributes not delivered as determined by Buyer in a commercially reasonable manner; provided, however, Buyer shall not be required to utilize or change its utilization of its owned or controlled assets or market positions to minimize Seller’s liability. “Replacement RA” means Resource Adequacy Benefits, if any, equivalent to those that would have been provided by the Facility with respect to the applicable Showing Month in all respects, including, as applicable, Resource Category and Flexible Capacity Category, and any successor criteria applicable to the Facility, unless Buyer consents to accept Replacement RA from another facility that provides non-equivalent Resource Adequacy Benefits. |
| Ancillary Services Capability: | The Facility will be able to provide the full suite of Ancillary Services in CAISO markets (to the extent any such services are available in the CAISO markets as of the Effective Date) and Seller will dispatch the Facility in response to signals from the Buyer or Buyer’s Scheduling Coordinator, subject to the Operating Restrictions. These Ancillary Services include Frequency Regulation, Spinning Reserve, Ramp Support, Frequency Response, Voltage Control, VAR Dispatch, and Power Factor Correction. Upon Buyer’s reasonable request, Seller shall submit the Facility for additional CAISO Certification so that the Facility may provide additional Ancillary Services that the Facility is, at the relevant time, actually physically capable of providing without modification of the Facility, provided that Buyer has agreed to reimburse Seller for any costs Seller incurs in connection with conducting such additional CAISO Certification. |
| Credit Requirements: | Seller shall post security as follows: Development Security – $125/kW of Storage Contract Capacity Performance Security – $105/kW of Storage Contract Capacity To secure its obligations under the ESSA, Seller shall deliver the Development Security to Buyer within thirty (30) days of the Effective Date. Development Security shall be in the form of cash or a Letter of Credit. To secure its obligations under the ESSA, Seller shall deliver Performance Security to Buyer on or before the Commercial Operation Date. Within five (5) Business Days following any draw by Buyer on the Development Security or the Performance Security, Seller shall replenish the amount drawn such that the security is restored to the applicable amount. |
| Monthly Settlement and Invoice: | #### Within ten (10) days after the end of each month of the Delivery Term, Seller shall send a detailed invoice to Buyer for the amount due for Product delivered during such month. The invoice shall include all information necessary to confirm the amount due. Payment for undisputed amounts shall be due to the applicable Party thirty (30) days from the invoice date, with disputed payments subject to Buyer’s billing dispute process. |
| Metering/Shared Facilities: | The Facility shall be separately metered from any other generation or storage facility and 100% of the output and services available from the Facility shall be conveyed to Buyer under the ESSA. Seller will provide and maintain at its sole expense separate metering and a separate CAISO resource ID for the Facility. Seller may share interconnection facilities with affiliates owning other generation or storage facilities, subject to commercially reasonable and customary shared facilities arrangements to be further described in the ESSA; provided that such agreements shall permit Seller to perform or satisfy, and shall not purport to limit, its obligations hereunder, including providing interconnection capacity for the Facility in an amount not less than the Storage Contract Capacity. |
| Guaranteed Storage Availability: | Ninety-eight percent (98%) |
| Availability Adjustment: | If the Monthly Storage Availability (as defined in the ESSA) during any month is less than the Guaranteed Storage Availability, Buyer’s payment for the Product shall be calculated using the “Availability Adjustment” or “AA”, which is calculated as follows: - If the Monthly Storage Availability is greater than or equal to the Guaranteed Storage Availability, then: AA = 100% - If the Monthly Storage Availability is less than the Guaranteed Storage Availability, but greater than or equal to 70%, then: AA = 100% - [(98% - Monthly Storage Availability) x 2] - If the Monthly Storage Availability is less than 70%, then: AA = 0 |
| Business Tax (SJCE only): | The Seller shall obtain a City business tax certificate or exemption, if qualified, and will maintain such certificate or exemption for the Delivery Term. |
| Workforce & Community Investment Obligations: (note: section required by Ava; requested by SJCE) | Seller must abide by any workforce and community investment obligation proposals included in its bid. Seller to provide commitments related to utilizing union workforce. [For Ava: Seller shall donate $____________ to Ava’s Community Investment Fund, with fifty percent (50%) due within sixty (60) days after the Effective Date of the ESSA, and fifty percent (50%) due on or before the Guaranteed Construction Start Date.] [Ava required language for projects outside Ava’s service territory] |
| No Recourse to Members of Ava: | Ava is organized as a Joint Powers Authority in accordance with the Joint Exercise of Powers Act of the State of California (Government Code Section 6500, et seq.) and is a public entity separate from its constituent members. Ava will solely be responsible for all debts, obligations and liabilities accruing and arising out of the ESSA. Seller will have no rights and will not make any claims, take any actions or assert any remedies against any of Ava's constituent members, or the officers, directors, advisors, contractors, consultants or employees of Ava or Ava's constituent members, in connection with the ESSA. |
| City of San José Designated Fund and Limited Obligations: | - Designated Fund. City of San José is a municipal corporation and is precluded under the California State Constitution and applicable law from entering into obligations that financially bind future governing bodies, and, therefore, nothing in the ESSA shall constitute an obligation of future legislative bodies of the City to appropriate funds for purposes of the ESSA; provided, however, that (i) City of San José has created and set aside a designated fund (the “Designated Fund”) for payment of its obligations under the ESSA and (ii) subject to the requirements and limitations of applicable law and taking into account other available money specifically authorized by the San José City Council and allocated and appropriated to the San José Clean Energy’s obligations, City of San José agrees to establish San José Clean Energy rates and charges that are sufficient to maintain revenues in the Designated Fund necessary to pay its obligations under the ESSA and all of City of San José’s payment obligations under its other contracts for the purchase of energy for San José Clean Energy. City of San José shall provide Seller with reasonable access to account balance information with respect to the San José Clean Energy Designated Fund during the Term. - Limited Obligations. City of San José’s payment obligations under the ESSA are special limited obligations of City of San José payable solely from the Designated Fund and are not a charge upon the revenues or general fund of the City of San José or upon any non- San José Clean Energy moneys or other property of the Energy Department or the City of San José. |
| Purchase Option: | Seller hereby grants Buyer the exclusive right, but not the obligation, to purchase the Facility at a price equal to the fair market value of the Facility determined in a commercially reasonable manner by a third-party independent evaluator (the “Purchase Option”). All costs related to the appraisal shall be borne by Seller. The Purchase Option may be exercised by Buyer by delivering notice to Seller at least twelve (12) months prior to the end of the Delivery Term, with closing to occur on the day after the last day of the Delivery Term. |
| Governing Law/Venue: | Governing Law: State of California Venue: [Alameda County][Santa Clara County] |
| Definitions: | The following terms, when used herein with initial capitalization, shall have the meanings set forth below: “Ancillary Services” means all ancillary services, products, functionalities, and grid-support attributes recognized by CAISO from time to time, including without limitation, Regulation Up, Regulation Down, Spinning Reserve, Non-Spinning Reserve, voltage support, frequency response, and any successor or similar services, that the Facility is capable of providing when operated in accordance with the terms and conditions of the ESSA, the Interconnection Agreement, applicable Law, the Operating Restrictions, and Prudent Operating Practice, whether or not such services are actively procured or compensated by CAISO at the relevant time. “Battery Energy Storage System” or “BESS” means the Energy Management Software and related storage equipment including but not limited to transformers, batteries, fire suppression, thermal management, enclosures, and inverters. “CAISO” means the California Independent System Operator. “CAISO Certification” means the certification and testing requirements for a storage unit set forth in the CAISO Tariff that are applicable to the Facility, including certification and testing for all applicable Ancillary Services, PMAX, and PMIN. “CAISO-Controlled Grid” has the meaning set forth in the CAISO Tariff. “CAISO Tariff” means the California Independent System Operator Corporation Agreement and Tariff, Business Practice Manuals (BPMs), and Operating Procedures, including the rules, protocols, procedures and standards attached thereto, as the same may be amended or modified from time-to-time and approved by FERC. “Capacity Attributes” means any current or future defined characteristic, certificate, tag, credit, or accounting construct associated with the amount of power that the Facility can discharge and deliver to the Delivery Point at a particular moment and that can be purchased and sold under CAISO market rules, including Resource Adequacy Benefits. “Charging Energy” means the energy delivered to the Facility pursuant to a Charging Notice as measured by the Facility Meter in accordance with CAISO metering requirements and Prudent Operating Practices, as such meter readings are adjusted pursuant to CAISO requirements for any applicable Electrical Losses. “Construction Start” will occur following Seller’s execution of an engineering, procurement and construction (EPC) contract related to the Facility and issuance of a full notice to proceed with the construction of the Facility under the EPC contract, mobilization to site by Seller and/or its designees, and includes the physical movement of soil at the site. “Contract Year” means a period of twelve (12) consecutive months. The first Contract Year shall commence on the Commercial Operation Date and the last Contract Year shall end at midnight at the end of the day prior to the anniversary of the Commercial Operation Date. “Discharging Energy” means all energy delivered to the Delivery Point from the Facility, net of Station Use, as measured by the Facility Meter in accordance with CAISO metering requirements and Prudent Operating Practices, adjusted pursuant to CAISO requirements for any applicable Electrical Losses. For the avoidance of doubt, all Discharging Energy will have originally been delivered to the Facility as Charging Energy. “Full Capacity Deliverability Status” has the meaning set forth in the CAISO Tariff. “Guaranteed Efficiency Rate” has the meaning set forth in the table above. “Letter(s) of Credit” means one or more irrevocable, standby letters of credit issued by a U.S. commercial bank or a foreign bank reasonably acceptable to Buyer with a U.S. branch, having assets of at least $10 Billion, with such bank having a credit rating of at least A- from S&P or A3 from Moody’s. “Minimum Efficiency Rate” means seventy-five percent (75%). “MW” means megawatts in alternating current, unless expressly stated in terms of direct current. “MWh” means megawatt-hour measured in alternating current, unless expressly stated in terms of direct current. “Operating Restrictions” means those rules, requirements, and procedures set forth in Exhibit A. “Qualifying Capacity” has the meaning set forth in the CAISO Tariff. “Round-Trip Efficiency Factor” means (a) if the Efficiency Rate is greater than or equal to the Minimum Efficiency Rate, one hundred percent (100%), or (b) if the Efficiency Rate is less than the Minimum Efficiency Rate, zero percent (0%). “San José Clean Energy” is the City of San José’s community choice aggregation program. The San José Energy Department administers and manages San José Clean Energy. “Scheduling Coordinator” has the meaning set forth in the CAISO Tariff. “Storage Capacity” means (a) the maximum dependable operating capability of the Facility to discharge electric energy that can be sustained for four (4) consecutive hours and (b) any other products that may be developed or evolve from time to time during the Term that the Facility is able to provide as the Facility is configured on the Commercial Operation Date and that relate to the maximum dependable operating capability of the Facility to charge and discharge electric energy. |

- Additional Term Sheet Provisions.

- Binding Effect. Notwithstanding anything herein to the contrary, this Section 2 is intended to be binding and enforceable, and no other provision of this Term Sheet shall be binding or give rise to any legal obligation unless and until a definitive ESSA has been approved as set forth above and executed and delivered by the Parties.

- No Obligation to Enter Into Proposed Transaction.  This Term Sheet is intended to provide an overview of the Proposed Transaction and is not intended to constitute a binding contract or an offer to enter into an ESSA with respect to the Proposed Transaction and does not obligate Buyer, Respondent or any party to enter into the Proposed Transaction or execute any agreement, including the ESSA, in connection with the Proposed Transaction.  Neither Buyer nor Seller will be deemed to have agreed to the ESSA or will be bound by any term thereof, unless and until authorized representatives of Buyer and Seller have executed final definitive documents, enforceable in accordance with their terms.

- Form of Agreement.  The ESSA shall be based on Buyer’s pro forma energy storage services agreement issued in connection with the RFO, as may be updated by Buyer prior to execution of the ESSA to reflect non‑economic, generally applicable, administrative, clarifying, conforming or regulatory changes. The definitive ESSA shall be revised as necessary to reflect the express terms set forth in this Term Sheet and to include the applicable provisions of Buyer’s pro forma ESSA to the extent not inconsistent with such express terms. In the event of an actual conflict between an express provision of this Term Sheet and the pro forma ESSA, the express provision of this Term Sheet shall control to the extent of such conflict. To the extent any matter is not expressly addressed in this Term Sheet, such matter shall be governed by the applicable provisions of the pro forma ESSA.

- No Economic Re-Trade.  For the avoidance of doubt, the Storage Rate, Product definition, Storage Contract Capacity, Guaranteed Efficiency Rate, Guaranteed Storage Availability, Delivery Term, and all other economic terms expressly set forth in this Term Sheet are intended to be final and shall not be modified, supplemented, or adjusted in the definitive ESSA, except as expressly agreed to in writing by Buyer in its sole discretion.

- No Financing, Tax, or Cost Pass-Through.  Buyer shall have no obligation to adjust the Storage Rate or any other economic term of the definitive ESSA to account for Seller’s financing arrangements, tax equity structure, capital costs, changes in financing markets, interest rates, or Seller’s expected returns or costs, except to the extent expressly provided in the definitive ESSA as approved by Buyer.

- Other Agreements.  In connection with this Term Sheet, Respondent shall execute that certain Exclusive Negotiating Agreement (“Exclusive Negotiating Agreement”) with Buyer and provide a Shortlist Deposit (as defined in such agreement) in accordance with the Exclusive Negotiating Agreement.  The Shortlist Deposit will be returned in accordance with, and subject to, the terms of the Exclusive Negotiating Agreement.

- Expenses.  Each of Buyer and Respondent will pay its own costs and expenses (whether internal or out-of-pocket, and whether for legal, financial, technical or other consultants, or other purposes) in connection with the Term Sheet and any definitive agreements.

- Termination.  This Term Sheet will terminate upon the earlier of (a) execution of the ESSA or (b) expiration of the Exclusivity Deadline (as defined in the Exclusive Negotiating Agreement), as such Exclusivity Deadline may be extended in accordance with the Exclusive Negotiating Agreement.

- Governing Law.  This Term Sheet is governed by, and construed in accordance with, the laws of the State of California.

- Prior Agreements.  This Term Sheet supersedes all prior communications and agreements, oral or written, between and among Buyer and Respondent regarding the subject matter herein contemplated.

- Assignment.  This Term Sheet will be binding upon and inure to the benefit of Buyer and Respondent and their respective successors and permitted assigns. Neither Buyer nor Respondent will assign, pledge or otherwise transfer this Term Sheet or any right or obligation under this Term Sheet without first obtaining the other Party’s prior written consent (which consent will not be unreasonably withheld, or delayed).

- No Consequential Damages.  IN NO EVENT SHALL BUYER OR RESPONDENT OR ANY OF THEIR AFFILIATES AND/OR REPRESENTATIVES BE LIABLE FOR ANY LOST OR PROSPECTIVE PROFITS OR ANY OTHER CONSEQUENTIAL, INCIDENTAL, SPECIAL, PUNITIVE, INDIRECT OR EXEMPLARY DAMAGES UNDER OR IN RESPECT TO THIS TERM SHEET.

[Signatures appear on the following page.]

Note: SJCE does not sign/countersign term sheets but does require Respondents to submit fully marked up files.

IN WITNESS WHEREOF, Buyer and Respondent have by their duly authorized representatives executed this Term Sheet as of the Effective Date.

| [AVA COMMUNITY ENERGY AUTHORITY, a California joint powers authority |  | [SELLER] |
| --- | --- | --- |
| By: ___________________________ Printed Name: _____________________ Title: ___________________________] |  | By: ___________________________ Printed Name: _____________________ Title: ___________________________ |

[Exhibit A follows this page]

EXHIBIT A

Operating Restrictions

| BESS Operating Restrictions: | Stored Energy Level: [XX] MWh Max / [0] MWh Min Charging & Discharging Power: [XX] MW Max / [0] MW Min State of Charge: [100]% Max / [0]% Min Dispatch Limits: [365/465] Cycle Equivalents per Contract Year Maximum continuous time at minimum Stored Energy: [24] hours |
| --- | --- |
| Energy Management Software: | Seller must provide remotely operable, 2-4 second timestamps, data historian (at least 5 years of storage), SCADA/AGC communication and operability. Applications/Modes: - Dynamic Voltage Support - Shifting - Regulation - Flexible Ramp - Spinning Reserve - ITC Compliance, if applicable |
| Other Operating Limits: | [Seller-specified, if applicable] |